## Sheet1
Project Plan for New Site Move | Project Plan for VRU
Friday 4th November
Confirmation of seating plan from Chuck
Must have tested the speed dial function on the SDX
Complete office layout plan in place
Monday 6th November
BT Engineers in to install Feature Line
Rental Phones should be delivered
Cable and RJ45 s' must be here
1 x annalogue line installed
Cable Office
Tuesday 7th November | Tuesday 7th November
3 x Analogue lines installed | Analogue line for Modem in
Configure laplink machine
Cable Office
Purchase Microwave and Ketle
Purchase Fridge
Purchase some cheap cups
Wednesday 8th November
New Network Server arrives
Get an Electrician in to supply power points
Swap out server at Manor Court
Thursday 9th November
Give out boxes to staff that are relocating
Set Up Network Server
Confgure Modem Server
Configure Laplink Server
Friday 10th November
Staff that are moving must have packed everything into boxes
Must have received Fax machine
Office Talk installation at new site
Saturday 11th November
Removal company moving desks and filing cabinets
Configure Speed Dial extensions for all staff that are moving
Configure email routing to the new site
Export all users and import them at new post office
Sunday 12th November
Removal company moving desks and filing cabinets
Monday 13th November
New Site Goes Live
PRAY!!!!!!!!!!